# Task Division — Talk-to-my-Data

Artefact Capstone 2026 | Case #1: Building a real-world Generative AI application

Rotation across all 4 pillars: everyone takes a different sub-task each pillar, so by Stage 3 everyone has touched data, AI, backend, and frontend. Tasks marked Required come directly from Artefact's brief — don't skip these. Tasks marked Stretch are what makes the project stand out, but are the first things to cut if the timeline gets tight.

Note: Stage numbering and pillar numbering are separate — Stage 0's tasks are 0.1-0.4, Stage 1's are 1.1-1.3, and each pillar's tasks restart at .1 within that pillar.

# Stage 0 — Prerequisites ✅ COMPLETE

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| 0.1 Cloud Setup (GCP project, CLI, service decisions) ✅ DONE | Raed | Complete | Closed |
| 0.2 Environment Setup (Python, venv, IDE, .gitignore) ✅ DONE | Muhammed | Complete | Closed |
| 0.3 Architecture Sketch v1 (Excalidraw) ✅ DONE | Amir | Complete | Closed |
| 0.4 Dataset & KPI Draft ✅ DONE | Fares | Complete | Closed |

Gate cleared: GCP project verified working end-to-end, environment documented, architecture sketch presented to Mark + Quinten, dataset downloaded and KPIs defined.

# Stage 1 — Contracts & Skeleton ✅ COMPLETE

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| 1.1 Write schema.md ✅ DONE | All (together) | Complete | Closed |
| 1.2 Write api.md ✅ DONE | All (together) | Complete | Closed |
| 1.3 Repo Skeleton (/src, /mock_data, /docs) ✅ DONE | All (together) | Complete | Closed |

Gate cleared: both contract files committed and rendering correctly, folder skeleton matches the plan.

# Stage 2 — Core Build

# Pillar 1 — Cloud & Data Platform ✅ COMPLETE

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| 1.1 Retail Data Cleaning & ETL ✅ DONE | Raed | Complete | Closed |
| 1.2 BigQuery Data Warehouse Setup ✅ DONE | Fares | Complete | Closed |

Gate cleared: real data queryable in BigQuery by everyone.

Note: 1.3 (IAM & Security) and 1.4 (Docker & Cloud Run) moved out of this pillar -- see Stage 3 and Stage 5.

# Pillar 2 — LLM & Text-to-SQL

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| 2.1 Dynamic Schema Injection ✅ DONE | Raed | Complete | Closed |
| 2.2 Few-Shot Prompting & Domain Lexicon | Amir | Stretch — not started | Sat, Sep 26 |
| 2.3 Self-Healing Query Feedback Loop ✅ DONE | Muhammed | Complete | Closed |
| 2.4 Ambiguity Resolution & Clarification ✅ DONE | Fares | Complete | Closed |

Gate: a plain-English question reliably produces correct SQL against real data — met by 2.1/2.3/2.4. 2.2 remains open as a stretch enhancement and does not block Pillar 3/4.

# Pillar 3 — Backend & Analytics Engine

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| 3.1 FastAPI Core Service Layer | Raed | Required | Sun, Sep 27 |
| 3.2 SQL Validation & Safety Guardrails | Muhammed | Required | Sun, Sep 27 |
| 3.3 Retail KPI Computation Engine | Amir | Required — brief asks for 2+ KPIs | Sun, Sep 27 |
| 3.4 Multi-Modal Response Formatter | Fares | Required | Sun, Sep 27 |

Gate: /ask endpoint works end-to-end, callable directly, no UI needed yet.

# Pillar 4 — Frontend UI, Benchmark & Delivery

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| 4.1 Streamlit Conversational Interface | Muhammed | Required | Sun, Oct 4 |
| 4.2 Dynamic Data Visualizations | Raed | Stretch | Sun, Oct 4 |
| 4.3 Golden Benchmark Evaluation Suite | Fares | Stretch (10-15 questions is fine) | Sun, Oct 4 |
| 4.4 Excalidraw Architecture & Client Deck | Amir | Required — named in the brief | Sun, Oct 4 |

Gate: a real question typed into the real UI returns a real, working answer.

# Stage 3 — Integration

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| Full Pipeline Integration (replace remaining mocks, test end-to-end) | All (together) | Required | Sun, Oct 4 |
| 1.4 Docker & Cloud Run Deployment (moved here from Pillar 1) | Muhammed | Required | Sun, Oct 4 |

Gate: the full system works start to finish, without anyone manually patching things together.

# Stage 4 — Dry Run Prep

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| Dry Run Deck + Rehearsal, presented to Mark + Quinten | All (together) | Required | Mon, Oct 5 |

Gate: feedback received, clear list of what to fix before the final.

# Stage 5 — Final Polish & Deployment

| Sub-task | Owner | Priority | Deadline |
| --- | --- | --- | --- |
| Full Cloud Run Deployment + Final Deck + Live Demo Rehearsal | All (together) | Required | Sun, Oct 18 |
| 1.3 IAM & Security Configuration (deferred from Pillar 1) | Amir | Stretch | Sun, Oct 18 |

Gate: live demo works, deck is ready, everyone knows their speaking part.